## Sheet1
| Tasks | Start Date | End Date | Person (Primary) | Person (Secondary) | Progress | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%
1 | OneScriptForMurders | 2016-03-14 | 2016-03-23 | Andy Sudarmadi | Siddhant Devaru
2 | OneScriptForPolitical | 2016-03-14 | 2016-03-23 | Kanishka Ragula | Siddhant Devaru
3 | OneScriptForBurglary | 2016-03-14 | 2016-03-23 | Vikrant Ragula | Kanishkha Ragula
4 | Coding for SuperClass | 2016-03-14 | 2016-04-12 | Kanishka Ragula | N/A
5 | Coding for MurderClass | 2016-03-14 | 2016-04-21 | Siddhant Devaru | Andy Sudarmadi
6 | LoadGameScreen | 2016-03-14 | 2016-03-23 | Naren Anandh | N/A
7 | Coding for BurglaryClass | 2016-03-14 | 2016-04-24 | Vikrant Ragula | Kanishka Ragula
8 | Coding for PoliticalClass | 2016-03-14 | 2016-04-25 | Kanishka Ragula | Siddhant Devaru
9 | Coding for EvidenceClass | 2016-03-14 | 2016-04-26 | Vikrant Ragula | Kanishka Ragula
10 | Coding for DetectiveSuperClass | 2016-03-14 | 2016-04-13 | Siddhant Devaru | N/A
11 | Coding for SuspectClass | 2016-03-14 | 2016-04-11 | Andy Sudarmadi | N/A
12 | Gui for TitleScren | 2016-03-14 | 2016-03-23 | Naren Anandh | N/A
13 | Gui for ScreenInbox | 2016-03-14 | 2016-03-23 | Naren Anandh | N/A
14 | Gui for StartScreen | 2016-03-14 | 2016-03-23 | Naren Anandh | N/A
15 | Instruction Screen | 2016-03-14 | 2016-04-13 | Vikrant Ragula | N/A
16 | CodingResearchOnInteractiveGUI | 2016-03-15 | 2016-03-23 | Siddhant Devaru | bar: 10% to 20%
17 | CodingResearchOnInteractiveGUI | 2016-03-15 | 2016-04-13 | Andy Sudarmadi
18 | CodingResearchOnReadingScript | 2016-03-15 | 2016-03-23 | Kanishka Ragula
19 | CodingForEntryPoint | 2016-03-15 | 2016-04-19 | Siddhant Devaru
20 | CodingForTitleScreen | 2016-03-20 | 2016-03-31 | Siddhant Devaru | bar: 10% to 70%
21 | Convert Scripts into txt files | 2016-03-31 | 2016-04-04 | Kanishka Ragula
22 | Coding for the initial screen coming out of the start screen | 2016-03-20 | 2016-01-02 | Siddhant Devaru
23 | Political + Murder Script | 2016-03-31 | -- | Naren Anandh | bar: 10% to 70%
24 | CodingResearchForImageIcon | 2016-03-20 | 2016-01-02 | Siddhant Devaru